## Dashboard
PROJECT TITLE | E-Learning TTS |  |  |  |  | STATUS KEY | PRIORITY KEY
PROJECT MANAGER | Phuong |  |  |  |  | Not Started | High
EPIC | Duyệt và quản lý nhân sự |  |  |  |  | In Progress | Medium
START DATE | 2023-01-14 |  |  |  |  | Complete | Low
DISPLAY WEEK | 1 |  |  |  |  | On Hold
SPRINT LENGTH | 30 |  |  |  |  | Overdue | Low
|  |  | PRIORITY | STATUS |  | Not Started
Api Duyệt |  |  | High | Not Started
Front end Duyệt |  |  | Low | Not Started
phân quyền Full stack |  |  | Low | Not Started
|  |  | Low | Not Started
|  |  | Low | Not Started
|  |  | Low | Not Started
Launch
FULL NAME | ASSIGNED DAY | DAY USED | AVAILABLE DAY REMAINING | BUGS | WOKING TIME
Lê Minh Phương | 12.875 | 3.3125 | 9.5625 | 0 | 0

## Lê Minh Phương
| WORKING TIME |  | 24.5 |  |  |  |  | Duyệt và quản lý nhân sự
[8 empty] | 2023-01-14 | [6 empty] | 2023-01-21 | [6 empty] | 2023-01-28 | [6 empty] | 2023-02-04 | [6 empty] | 2023-02-11
GENERAL INFO |  |  |  |  | COMMENT |  |  | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | STATUS KEY | TYPE | PRIORITY KEY
TASK | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | TYPE OF TASK | EXECUTOR 'S ASSESSMENT | FEEDBACK OF EXECUTOR | FEEDBACK OF PM | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | Not Started | Task | High
14 | 12.875 | 3.3125 | 9.5625 | 0 |  |  |  | 2 | 0 | 3 | 3 | 1.5 | 3 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress | Bug | Medium
Viết tài liệu đặc tả cho phần mềm | 20 | 3 | 17 | Task | In Progress |  |  | 2023-01-14: 2; 2023-01-17: 1 | Complete |  | Low
Viết file elsx quản lý theo Alige | 4 | 3 | 1 | Task | Complete |  |  | 2023-01-16: 3 | On Hold
API đăng nhập | 6 | 0 | 6 | Task | In Progress | [37 empty] | Overdue
Giao diện đăng nhập | 2 | 0 | 2 | Task | Not Started
API đăng kí | 2 | 2.5 | -0.5 | Task | Complete |  |  | 2023-01-17: 2; 2023-01-18: 0.5
Giao diện đăng kí | 2 | 0 | 2 | Task | Not Started | [37 empty] | Complete |  | High
Phân quyền fullstack | 40 | 5 | 35 | Task | In Progress |  |  | 2023-01-20: 5
Giao diện menu | 5 | 0 | 5 | Task | In Progress
API thêm quản trị viên | 1 | 1 | 0 | Task | Complete | bar: 2023-01-18
API đăng xuất | 1 | 1 | 0 | Task | Complete | bar: 2023-01-20
API thêm thực tập sinh | 2 | 1 | 1 | Task | Complete | bar: 2023-01-20
API đăng nhập | 6 | 6 | 0 | Task | Complete |  |  | 2023-01-20: 6
Giao diện footer | 2 | 2 | 0 | Task | In Progress |  |  | 2023-01-19: 2
Giao diện trang chủ | 10 | 2 | 8 | Task | In Progress | bar: 2023-01-19 to 2023-01-20
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
|  |  |  | Task | Not Started

## Blank
| WORKING TIME |  | 0 |  |  |  |  | Duyệt và quản lý nhân sự
[8 empty] | 2023-01-14 | [6 empty] | 2023-01-21 | [6 empty] | 2023-01-28 | [6 empty] | 2023-02-04 | [6 empty] | 2023-02-11
GENERAL INFO |  |  |  |  | COMMENT |  |  | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | STATUS KEY | TYPE | PRIORITY KEY
TASK | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | TYPE OF TASK | EXECUTOR 'S ASSESSMENT | FEEDBACK OF EXECUTOR | FEEDBACK OF PM | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | Not Started | Task | High
0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress | Bug | Medium
| 0 | 0 | 0 | Task | Not Started | [37 empty] | Complete |  | Low
| 0 | 0 | 0 | Task | Not Started | [37 empty] | On Hold
| 0 | 0 | 0 | Task | Not Started | [37 empty] | Overdue
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started | [37 empty] | Complete |  | High
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
|  |  |  | Task | Not Started

## Nhiệm vụ-BA
| WORKING TIME |  | 0 |  |  |  |  | Duyệt và quản lý nhân sự
[8 empty] | 2023-01-14 | [6 empty] | 2023-01-21 | [6 empty] | 2023-01-28 | [6 empty] | 2023-02-04 | [6 empty] | 2023-02-11
GENERAL INFO |  |  |  |  | COMMENT |  |  | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | STATUS KEY | TYPE | PRIORITY KEY
TASK | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | TYPE OF TASK | EXECUTOR 'S ASSESSMENT | FEEDBACK OF EXECUTOR | FEEDBACK OF PM | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | Not Started | Task | High
1 | 0.5 | 0 | 0.5 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress | Bug | Medium
Vẽ luồng và viết mô tả luồng đăng kí,đăng nhập | 4 | 0 | 4 | Task | Not Started | [37 empty] | Complete |  | Low
| 0 | 0 | 0 | Task | Not Started | [37 empty] | On Hold
| 0 | 0 | 0 | Task | Not Started | [37 empty] | Overdue
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started | [37 empty] | Complete |  | High
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
|  |  |  | Task | Not Started

## Nhiệm vụ-Tester
| WORKING TIME |  | 0 |  |  |  |  | Duyệt và quản lý nhân sự
[8 empty] | 2023-01-14 | [6 empty] | 2023-01-21 | [6 empty] | 2023-01-28 | [6 empty] | 2023-02-04 | [6 empty] | 2023-02-11
GENERAL INFO |  |  |  |  | COMMENT |  |  | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | STATUS KEY | TYPE | PRIORITY KEY
TASK | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | TYPE OF TASK | EXECUTOR 'S ASSESSMENT | FEEDBACK OF EXECUTOR | FEEDBACK OF PM | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | Not Started | Task | High
1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress | Bug | Medium
Viết testcase đăng nhập | 0 | 0 | 0 | Task | Not Started | [37 empty] | Complete |  | Low
| 0 | 0 | 0 | Task | Not Started | [37 empty] | On Hold
| 0 | 0 | 0 | Task | Not Started | [37 empty] | Overdue
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started | [37 empty] | Complete |  | High
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
| 0 | 0 | 0 | Task | Not Started
|  |  |  | Task | Not Started

## Tester-Blank
Project name | E-Learning TTS |  |  | Status | Number of task |  | Fixed | Number of task |  | PRIORITY KEY |  | DEV FIX
Module name | Đăng nhập |  |  | PASS | 0 |  | Not Started | 34 |  | High |  | Not Started |  |  |  | PASS
Created by | Phương |  |  | FALSE | 34 |  | In Progress | 0 |  | Medium |  | In Progress |  |  |  | FALSE
Createtion Date |  |  |  | REOPEN | 0 |  | Complete | 0 |  | Low |  | Complete |  |  |  | REOPEN
Reviewed by | [6 empty] | On Hold | 0 |  |  |  | On Hold |  |  |  | FALSE
Reviewed date | [6 empty] | Overdue | 0 |  |  |  | Overdue
Test scenario ID | Test scenario Description | Test Case ID | Test Case Description | Test steps | Preconditions | Test data | Expect result | Actual result | Status | Priority | Note - Test | Dev fix | Assign to | Comment | Ngày fixed
[9 empty] | FALSE | High |  | Not Started | Lê Minh Phương
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started
[9 empty] | FALSE | High |  | Not Started